## SEMANA 7
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Orlando Godoy | What did you do yesterday? | Analicé HU-033 y diseñé la vista de agenda semanal. | Implementé lógica de carga de sesiones y estados en la agenda. | Finalicé pruebas de HU-033 y empecé HU-055 con diseño de resumen mensual. | Implementé filtros por usuario y exportación en HU-055. | Inicié HU-056 con redirección automática y temporizador funcional.
| What are doing today? | Comenzaré con la interfaz de agenda semanal. | Integraré backend con la vista de agenda. | Validaré datos y prepararé entorno para HU-055. | Finalizaré HU-055 y prepararé pruebas. | Ajustaré temporizador y lógica de cierre automático en HU-056.
| Is there anything blocking you? | No. | No. | Dudas menores sobre formato de exportación, ya resueltas. | No. | No.
Felipe Rios | What did you do yesterday? | Inicié el desarrollo del sistema para agrupar recordatorios de sesiones y tareas. | Implementé el panel de estadísticas del administrador con número de sesiones, pacientes activos y tareas asignadas.
| What are doing today? | Diseñar la estructura de los recordatorios | Realizar pruebas.
| Is there anything blocking you? | No. | No.
Miguel Román | What did you do yesterday? |  | Funcionalidad de reagendar citas | Terminar funcionalidad de reagendar | Creacion de pdf de agenda diaria | Funcionalidad de chat
| What are doing today? | Funcionalidad de reagendar citas | Terminar funcionalidad de reagendar | Creacion de pdf de de agenda diaria | Funcionalidad de chat | Seguir programando funcionalidad de chat
| Is there anything blocking you? | No
[Name] | What did you do yesterday?
What are doing today?
Is there anything blocking you?

## SEMANA 8
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
Miguel Román | What did you you do yesterday? | Funcionalidad de chat | Funcionalidad de chat | Funcionalidad de chat
| What are doing today? | Funcionalidad de chat | Funcionalidad de chat | Término de funcionalidad
| Is there anything blocking you? | Desconexión entre backend y frontend, no envío de mensajes | No | No
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION

## RESOURCES
Useful resources
Burndown Chart Template
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel