## SEMANA 9
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Orlando Godoy | What did you do yesterday? | Se revisaron los requerimientos de HU-49 y se definieron los componentes del dashboard. | Se implementaron las visualizaciones de sesiones por psicólogo y horas efectivas trabajadas. | Se completaron las visualizaciones de pacientes atendidos y estado de tareas. | Se realizaron pruebas funcionales del dashboard y ajustes visuales. | Se documentó la HU y se presentó el dashboard al equipo.
| What are doing today? | Planificación y asignación de tareas para HU-49. | Continuar desarrollo del dashboard. | Finalizar desarrollo y comenzar pruebas. | Validar criterios de aceptación y corregir detalles. | Cierre de HU-49.
| Is there anything blocking you? | No. | No. | No. | No. | No.
[Name] | What did you do yesterday?
What are doing today?
Is there anything blocking you?
Miguel Román | What did you do yesterday? |  | Registro de progreso entre usuarios | Registro de progreso entre usuarios | Exportar información de dashboard en pdf | Exportar información de dashboard en pdf
| What are doing today? | Registro de progreso entre usuarios | Finalizacion de funcionalidad | Exportar información de dashboard en pdf | Exportar información de dashboard en pdf | Exportar información de dashboard en pdf
| Is there anything blocking you? | No | No | No | No | No
[Name] | What did you do yesterday?
What are doing today?
Is there anything blocking you?

## SEMANA 10
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Orlando Godoy | What did you you do yesterday? | N/A | N/A | N/A | N/A | N/A
| What are doing today? | N/A | N/A | N/A | N/A | N/A
| Is there anything blocking you? | N/A | N/A | N/A | N/A | N/A
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
Miguel Román | What did you you do yesterday? | Exportar información de dashboard en pdf | Modificar Bases de datos post revisión docente | Modificar Bases de datos post revisión docente
| What are doing today? | Modificar Bases de datos post revisión docente | Modificar Bases de datos post revisión docente | Modificar Bases de datos post revisión docente
| Is there anything blocking you? | Claves foráneas | No | No
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION